## Sheet1
Project | Orion
Date | Milestone | Task | Assets to be created | %Complete | Comments
2019-01-16 | Design
|  | Chose a game | None | 100
|  | Modify design documentations | None | 100
2019-01-31 | Design II
Planing Sechdule
|  | Create Tech Design Document | None | 100
|  | Divide feature list for the Demo | None | 100
2019-02-07 | Demo Features
Basic Combat System
Create Basic Units
|  |  | Create 2 (1 mele and 1 range) sample models (including hp bar) | 100
|  |  | Movement script | 100
|  |  | Attack and targeting system | 100
|  |  | Health display and calculation scripts | 100
Create Basic Buildings
|  |  | Create 1 (range attack) Building model (including hp bar) | 100
|  |  | Attack and targeting system | 100
|  |  | Health display and calculation scripts | 100
Create Base and energy generation system
|  |  | Create 1 Base model | 100
|  |  | Health display and calculation scripts | 100
|  |  | Energy display and generation scripts | 100
|  | Create Basic Map | Create 1 basic sample map model for testing purpose (with only 1 lane) | 100
|  | Create Basic Gamemanager | Scripts managing turn timer, phases, energy cost, and spawn units | 100
Basic Control System and UI
|  | Create Basic Control System | Scripts | 100
|  |  | Input Handling | 100
Create Basic Card Display
|  |  | Card Game object interactable and created | 100
|  |  | 4 sample cards images | 100
Energy bar and timer
|  |  | Energy Bar created and works | 10
|  |  | Timer reflects change in time and stops at 0 | 30
| Testing Demo | Implementing the Q/A test plan |  | 0
2019-03-06 | Trying to Complete the Vertical Slice
| "The integration of Game manager and the UI system was delayed." | Complete the current basicversion of Game Manager | Scripts | 100
|  | Intergate UI system | Unity Editor Setting and Scripts | 100
| Testing Finished Demo | Impelenting the Q/A test plan
2019-03-28 | Alpha Development Phase I(Delayed)
Adding more features
Background Music and Interiaction Music
|  |  | Adding Background music to the game | 100
|  |  | Adding attack, death music for units | 100
Creating extra units
|  |  | Create 3(1 support, 1 mele AOE attack, and 1 healing) new units models | 66(Abandoed the AOE attack minion) | Running out of time
|  |  | Support unit script | 100
|  |  | Mele AOE attack script | 0 | Abandoned
|  |  | Healing script | 100
|  |  | 3 new card images | 66 | Finished 2
Creating full size 3 lanes map
|  |  | Create a map with 3 separate lane | 100
|  |  | Multilple lanes intereaction script for units | 0 | Abandoned due to running out of time
Create 2 special cards
|  |  | Create 2 (1 damage, 1 action phase time manipulation)special cards which could be used during action phase | 100
|  |  | Special card scprits | 100
|  |  | 2 new card images | 100 | Finished images, but decided to use buttons instead
|  | Creating extra buildings |  |  | Abandoned due to running out of time fixing exsiting building scripts
|  |  | Create 2 (1 unit generation camp, and 1 energy generating)new buildings models | 50 | Unit Generation Dropped
|  |  | unit generation script | 0
|  |  | 2 new card images | 50
2019-04-11 | Alpha Development Phase II
Create Basic Deck Selection System
|  | Implementing Basic pre-game Deck Selection System | Implementing a basic system that Player can select their battle card set before the match | 0 | Abandoned due to running out of time and limited number of cards reduce the priority of this system
|  | Expand the UI system | Creating main menu, battle menu, and card selection menu | 100
|  | Expand the Game Manager | Revising the script to support the pre-game card selection system | 100
2019-04-22 | Beta Development Phase I
Deck System
|  | Deck and Card Scripts | Implementing a system which allows each players to have random new card after using existing hand | 100
| Modify the music mixing SFX | Balance the musics to make the sound less annoying | Seting the SFX of unity editor