## Sheet1
Ref # | System Name | Feature Supported | Feature Specifics | New or Modified Code | Priority | Difficulty | Risk | Time Estimation | Comments
F001 | Combat System
F001a |  | Units | 2 types of infantry units | New | High | Med | Low | 2 weeks
F001b |  | Buildings | 2 types of buildings with different attacks | New | High | Med | Low | 2 weeks
F001c |  | Special Attack | 1 special attack | New | Medium | High/Med | Low | 2 weeks
F002 | Card System
|  | Design Cards | Design the cards | Modified from the internet | High | Med | Med | 1 week
F002a |  | Pre-battle | Card set selection |  | Low | Med | High | N/A
F002b |  | In-battle | Choosing cards to play in the moment | New | High | Med/High | Med | 2-3 weeks
F003 | Winning Conditions
F003a |  | Base health comparison |  |  | High | Low | Low | 1 week
F003b |  | Zero base health |  |  | High | Low | Low | 1 week
F004 | Map System
F004a |  | Lanes | 3 lanes | New | Med | Low | Low | 1 week
F004b |  | Base | 1 base per player | New | High | Low | Low | 1 week
F004c |  | Building locations | 2 locations | New | High | Low | Low | 1 week
F005 | Energy System
|  | Default Generation | 3 energy/sec | New | High | Low | Low | 1 week
|  | Generation through damage | 1 energy/damage | New | High | Med | Med | 2 week
F007 | Animations System | Animation System were removed due to lack of skills for creating 3D animations. Some (eg: attack) were partially implemented via object movement
|  | Card selection | Card flipping/ moving onto map | New animation | Med | Med | High | 2 week
|  | Unit movement and combat | stationary, walking/moving and attacking animations on characters | New animation | Med | Med | Med | 2 week
|  | Buildings and combat | Construction, and effects of building animation | New animation | Med | Med | Med | 2 week
|  | Special attack and combat | Map-wide effect animation of special attack | New animation | Med | Med | Med | 2 week
F008 | Deck storage
|  | Card set customizer | Changing the cards you use in game | New | Low | High | High | 2 week
F009 | Turn system
|  | Turn timer | 10 seconds in decision phase, 10 seconds in action phase | New | High | Low | Low | 1 week
|  | Turn counter | 30 turns | New | High | Low | Low | 1 week
F010 | UI System
|  | Unit placement | Spawning units into specified lane | New | High | Med | Low | 2 weeks
|  | Building placement | Placing building in specified spot | New | Med | Med | Low | 1 week
|  | Card set selection | Main menu card set selection | New | Low | High | High | N/A
|  | Card set customizer | Main menu card set customization | New | Low | High | High | N/A
|  | Health bars | Health bars on every placeable game component | New | High | Low | Low | 1 week
|  | Music | Background Music, card selection, simulation sounds | New | Low | Med | Low | 2 weeks
|  | Energy bar | Energy bar on player's screen | New | High | Low | Low | 1 week