## Sheet1
Risk Register
|  | Area of Risk |  |  | Status | Probability | Impact | Priority | Mitigation | Recovery
ID # | Name | (Discipline or Feature) | Quick Description | Owner | (Open/Closed) | (1-5) | (1-5) | (Prob. * Impact) | (How to reduce/remove the risk) | (How to fix the problem if it occurs)
1 | Staff | Team | Loss of staffing | Jeremy | Open | 1 | 4 | 4 | Make sure everyone is listened to and is happy with the class/project. | Make sure everyone understands what all the tasks are in case they need to fill in, put multiple people on each task
2 | Project Data | Team | Loss or corruption of data | Jeremy | Open | 3 | 4 | 12 | Always have back-ups of project in case current version is corrupted | Ideally retrieve back-up, or redo the portion that was corrupted (worst case scenario)
3 | Art/Animation | Team | Having no models/artwork for our project |  |  | 3 | 1 | 3 | Learn to create models/animations through tutorials | Attempt to learn or use free models online or on Unity (worst case scenario)